## Sheet1
Task Name | Estimate | Start Date | Task Owner | Assumptions / Known Issues / Notes
Project Problem Statement | 1 days | 2019-11-10 | Josh Griffith
Project Plan | 1 days | 2019-11-11 | Josh Griffith
Get Project Approved | 3 days | 2019-11-12 | Jason Jenkins
Research Federal Tax Laws | 7 days | 2019-11-12 | Josh Griffith
Design Classes | 1 days | 2019-11-19 | Josh Griffith
Document Technical Design | 1 days | 2019-11-20 | Josh Griffith | Include version control system, language, IDE, etc.
Write code for features | 2 days | 2019-11-21 | Josh Griffith
Wrtie Test Cases | 1 days | 2019-11-22 | Josh Griffith | Need to create different users at different with different tax requirmnets
Finalzie Code | 1 days | 2019-11-23 | Josh Griffith
Code Review | 1 days | 2019-11-24 | Josh Griffith | Need to compare results I got with other tax accountants like H and R Block, Turbo Tax, etc.
Test Code - Development | 3 days | 2019-11-25 | Josh Griffith
Deploy Program | 1 days | 2019-11-29 | Josh Griffith | Acquire Test Data
Test Deployment | 1 days | 2019-11-30 | Josh Griffith
Fix Issues | 10 days | 2019-11-30 | Josh Griffith
Submit Program | 0 days | 2019-12-10 | Josh Griffith
Write development log | 0 days |  |  | this will be on on going process